## Sheet1
Task Num | Assigned to | Task | ETA | Completed? | Completion Date | Moved to prod? | Priority | Notes
1 | Kusum | Alok to modify Excel file for Mootly Products. | 2013-07-09 | Yes | 2013-07-09 | Yes
2 | Priyank | Only allow Personal or HUF return by restricting PAN numbers when entering PAN numbers. Message should be displayed – Alok to OK the message | 2013-07-09 | Yes | 2013-07-08 | Yes
3 | Abhishek | Make changes to pension screen based on Alok’s input | 2013-07-09 | Yes | 2013-07-08 | Yes
4 | Megha | Make final changes to House Income Screen based on Alok’s input. Megha to correct/fix bugs on the screen – state, tax computation, calculation of balance | 2013-07-09 | Yes | 2013-07-11 | Yes
5 | Abhishek | Under Other Source of income: Put in check on Total Taxfree Incomes. If greater than Rs. 5000/- put in message that ITR1(Basic) cannot be used. User Deluxe(ITR2). Mmake sure it is taken into consideration for tax computation based on Alok’s input. | 2013-07-09 | Yes | 2013-07-11 | Yes
6 | Alok | In deductions Alok to verify whether drop down under each section are correct | 2013-07-09
7 | Amit | In deductions put in text box to capture detail if Other is selected | 2013-07-09 |  |  |  |  | AP - July 7th Fixed
8 | Dhananjay | Fix un-necessary hyperlink in Summary page | 2013-07-09 | Yes | 2013-07-10 | Yes
9 | Pankaj | In advance tax, Pankaj to correct text “Date of Credit into Govt. Account *” to “Date of Deposit into Govt. Account " | 2013-07-09 | Yes | 2013-07-09 | Yes
10 | Priyank | Modify drop down list, and store documents based on Alok's input for documents required for each package | 2013-07-09 | Yes | 2013-07-10 | Yes
11 | Priyank | After filing details, and continuing return, if eFile is not available, it should show Upload documents button right there | 2013-07-09 | Yes | 2013-07-09 | Yes
12 | Megha | ITR1.whocan/ITR1.whocannot text to be finalized after talking to Alok. Make sure it is shown on home page, pricing and when selection of package is done during personal information entry | 2013-07-09 | Yes
13 | Priyank | On pricing page -> Additional services should have hypelink, which should also be shown on home page under "Additional Services". Home oage additional services should be superset of additional services on pricing page | 2013-07-09 | Yes | 2013-07-11 | Yes
14 | Amit | Privacy policy | 2013-07-09 |  |  |  |  | AP Send the text
15 | Amit | Terms of use | 2013-07-09
16 | Amit | About US | 2013-07-09 | Yes | 2013-07-12 | No
17 | Amit | Contact US | 2013-07-09
18 | Amit | FAQ | 2013-07-09
19 | Priyank | Capture password for document uploaded if password protected | 2013-07-09 | Yes | 2013-07-11 | Yes
20 | Pankaj | Download xml on itReturn home page() | 2013-07-09 |  |  |  | P2 | AP - July 7th Fixed We still have a long way to go with eCommerce integration.
21 | Alok | CCAvenue Registration | 2013-07-09
22 | Amit | Activation Code is not working.Resolve issue | 2013-07-09 |  |  |  |  | AP - July 14th Fixed. Kusum please retest.
23 | Amit | Upload Xml to It return Website | 2013-07-10 |  |  |  |  | AP - July 14th I have spent lot of time on this one with no real progress. My suggestion is to work hard to get the intermediatary status and work on a proper integraton.
Added Queries by Nandini and Amit Kumar Ranjan
Summary/ Computation PDF Sheet
24 | Amit | Summary Sheet (PDF) which is mailed or Downlaoded to/ by user is not in a proper Format. | 2013-07-13 |  |  |  | P3 | AP - July 14th Lets work on it when we are done with ITR2
| Amit | If there is no Value in any heads then in Summary, the details should not show in Value as "0" instead completely hide it. | 2013-07-13 |  |  |  | P3 | AP - July 14th Need to double check with DJ
EZ File
25 | Amit | In the screen of "Individual Information", after selecting the package and mode when I save, it shows, SSL Connection Error, but it should be directed to the "eZ file Upload" screen. But now the eZ file upload screen is shown from the screen when we select "Continue filing" in Action Option. | 2013-07-13 |  |  |  |  | AP - July 14th I believe it was a configuration error. Please test it again.
26 | Amit | If by mistake User enters his PAN no. or Last Name wrongly, then it s not editable in fututre Steps So user should be given an Option to Edit or delete the Assessee details should be available before he files return and after filing edit and Delete option should not be given to the user. | 2013-07-13 |  |  |  | P4 | AP - July 14th This will be revisited once we are live.
27 | Amit | In Ez file upload Documents List theres is no need of Sub heading of Sources, Just the Documents list is enough. And there must be an option of OTHERS, were user will upload documents which were not listed and option to mention the details of the Documents uploaded. (Multiple times upload option should be available.) | 2013-07-13 |  |  |  | P3 | AP - July 14th Fixed and comments There are multiple issues in this issue. Let me try to address 1 at a time. Remove the drop down - Lets keep it for now and then we can remove it at a later date. Multiple Upload - Will be done at later date Add others to the list - This can be solved by adding others as a type under Others Notes - Fixed. Added as a separate field.
Form 16
28 | Amit | TAN No. is Mandatory when the user fills the TDS details in Form 16. but if user doesn’t fills the TDS form 16 then the return should be processed. | 2013-07-13 |  |  |  | P3 | AP - July 7th Can we keep it as is, it will take some time to do impact analysis for this. Also what is the probability that the user will have a FORM 16 without the TAN #? Please let me know, we can then decide on the urgency of this.
29 | Amit | In Form 16 The Employee Name which is Autofill doesn’t Show the Middle Name (Only First & Last Name is shown) | 2013-07-13 |  |  |  | P3 | AP - July 14th Fixed
30 | Amit | In case of Form 16, When user selects Others in Employer Category the 4. Deductions "Entertainment Tax and Professinal Tax" is hided. Which is wrong Practise | 2013-07-13 |  |  |  | P1 | AP - July 14th Fixed
| Amit | If user selects Govt as Employer Category then the Entertainment allowances allowed Is lower of the User entry or Rs.5000. This option should be hided as it is not applicable in case of Others and PSU. | 2013-07-13 |  |  |  | P1 | AP - July 14th Fixed
| Amit | If user Selects any of the employee category then Professional Tax will be the lower of Rs. 2500 or the User entry. | 2013-07-13 |  |  |  | P1 | AP - July 14th Fixed
31 | Amit | The Total of Deduction of Point 4 in Form 16 would be the maximum to the limit of Rs. 7500 only. | 2013-07-13 |  |  |  | P1 | AP - July 14th Fixed
32 | Amit | The Term 4(b) of Form 16 should be changed to “Tax on Employment/ Professional Tax” | 2013-07-13 |  |  |  | P1 | AP - July 14th Fixed
33 | Amit | In case of Calenders mentioned in various places, user should be given an option to edit by himself, (Like he could enter the date by himself) | 2013-07-13 |  |  |  | P3 | AP - July 14th I want to understand more on this issue. I was able to enter the data using keyboard. I would keep it as is for now. We can revisit it later.
House Property
34 | Amit | If user enters amount more than Rs. 180000 in Lettable Value then user needs to fill the PAN no. of Tenant. | 2013-07-13 |  |  |  | P1 | AP - July 14th Fixed
35 | Amit | When a user Opts for the "Property Co Owned" as YES, the user must fill atleast one co owner details and his share would be less then 100%. | 2013-07-13 |  |  |  | P1 | AP - July 14th Fixed
Deductions
36 | Amit | If a user Enters Bank Interest in Savings Bank Account (In Other Income Screen, Interest Taxable) that should be allowed as Deduction Under Section 80TTA. (Maximum Deduction is Rs. 10000) | 2013-07-13 |  |  |  | P1 | AP - July 14th Fixed
37 | Amit | In case of Deduction Under Section 80GG Remove the Backend Calculation. The Deduction will be the Rs. 24000 or The User entry which is lower. | 2013-07-13 |  |  |  | P1 | AP - July 14th Fixed